## Issue Register
PitchDeck - Code Review Issue Register
Repo: github.com/NikhileshU/PitchDeck ¦ 6 review rounds, 43062a6 -> da764c2 (phase-6-report) ¦ Updated 12 Aug 2026. Severity and status as assessed by the reviewer.
ID | Round | Commit reviewed | File | Location | Severity | Category | Issue | Status | Closed in
R1-C1 | 1 | 43062a6 | render_html.py | _chart_bar / _vmax (114-117) | Critical | Correctness | Negative bar values silently dropped. Probe values=[-5,10] emitted 1 path, expected 2. | Fixed | 4abca60
R1-C2 | 1 | 43062a6 | render_html.py | _chart_line (154-165) | Critical | Correctness | Single negative line point plotted off-canvas: cy=569.6 in a viewBox of height 320. | Fixed | 4abca60
R1-C3 | 1 | 43062a6 | themes/base.css | .card (~48) | Critical | Correctness | overflow:hidden clips, contradicting card-schema.md section 5 'do not clip'; no type ramp implemented. | Fixed | 4abca60
R1-C4 | 1 | 43062a6 | export_pdf.py | export (52) | Critical | Correctness | Stale-PDF false pass: output never unlinked, so a previous run's PDF satisfies both the size and %PDF- checks. | Fixed | 4abca60
R1-H5 | 1 | 43062a6 | render_html.py | main (343-344) | High | Correctness | Missing base.css fails open - renders an unstyled deck and exits 0. | Fixed | 4abca60
R1-H6 | 1 | 43062a6 | render_html.py | _resolve_images (325-331) | High | Correctness | 'Self-contained HTML' claim false: src rewritten to absolute local paths, breaks off-machine. | Fixed | 4abca60
R1-S1 | 1 | 43062a6 | render_html.py | _chart_svg (101,105) | Suggestion | Correctness | Bare tracebacks on bad IR: ZeroDivisionError on empty values, KeyError on unknown block/chart type. | Fixed | 4abca60
R1-S2 | 1 | 43062a6 | render_html.py | _chart_pie (186-188) | Suggestion | Correctness | Pie silently uses series[0] and discards the rest; IndexError on empty series; negatives produce nonsense arcs. | Fixed | 4abca60
R1-S3 | 1 | 43062a6 | render_html.py | _resolve_images (325-331) | Suggestion | Correctness | Mutates the loaded IR in place; corrupting if deck.json is ever re-serialised. | Fixed | 4abca60
R1-S4 | 1 | 43062a6 | render_html.py | _legend / _chart_hbar (69-77,128,144) | Suggestion | Correctness | Text overflow unhandled: legend has no wrap or width cap; long hbar category labels run off the left edge. | Fixed | 8d313de
R1-S5 | 1 | 43062a6 | render_html.py | _chart_hbar (144) | Suggestion | Style | hbar labels every bar unconditionally while bar applies a label_all = m*n <= 8 density guard. | Open
R1-S6 | 1 | 43062a6 | export_pdf.py | export (43-51) | Suggestion | Correctness | No virtual-time budget or compositor flag; find_browser uses .exists() rather than os.access(X_OK). | Fixed | 4abca60
R1-S7 | 1 | 43062a6 | export_pdf.py | export (51-54) | Suggestion | Correctness | Non-zero browser exit surfaced only when the file check fails. | Fixed | 4abca60
R1-S8 | 1 | 43062a6 | render_html.py | _css_vars (37-60) | Suggestion | Security | Theme values interpolated into <style> unescaped; a crafted value could break out of the block. | Fixed | 4abca60
R1-S9 | 1 | 43062a6 | render_html.py | _b_callout / _b_image (261,270) | Suggestion | Correctness | tone and fit become class names unvalidated; an unknown value renders unstyled with no error. | Fixed | 4abca60
R1-S10 | 1 | 43062a6 | CLAUDE.md | invariant 3 | Suggestion | Maintainability | render() signature deviates from the documented 3-arg contract (css kwarg undocumented). | Fixed | 4abca60
R1-S11 | 1 | 43062a6 | evals/ | - | Suggestion | Test coverage | No tests and no golden outputs at phase 4; phases 5, 6 and 9 would be written against unpinned output. | Fixed | 2eb086e
R2-H1 | 2 | 4abca60 | render_html.py | _cssv (~30) | High | Security | Denylist hole: url(http://...) and 'red; --color-text: red' both allowed, enabling a remote fetch during PDF export. | Fixed | 8d313de
R2-H2 | 2 | 4abca60 | .claude/settings.local.json + CLAUDE.md | whole file | High | Maintainability | Unrelated tooling config committed to a public repo; 84-line dgc-policy block contradicts invariant 10 and leaks local paths. | Fixed | 8d313de
R2-H3 | 2 | 4abca60 | base.css / export_pdf.py | - | High | Correctness | PDF still clips silently: @page fixed at 1280x720px with no cards==pages assertion. | Fixed | 8d313de
R2-S1 | 2 | 4abca60 | render_html.py | _legend | Suggestion | Correctness | _trunc(name,18) reduces but does not bound legend width; no cumulative width clamp, no series cap. | Fixed | 8d313de
R2-S2 | 2 | 4abca60 | render_html.py | _embed_images | Suggestion | Performance | No size guard and no dedup; the same image is base64-encoded once per card. | Fixed | 8d313de
R2-S3 | 2 | 4abca60 | render_html.py | _embed_images | Suggestion | Maintainability | Image resolution diverges for phase 9: python-pptx add_picture needs a path or stream, not a data URI. | Open
R2-S4 | 2 | 4abca60 | render_html.py | _block | Suggestion | Maintainability | Broad except re-labels genuine renderer bugs as IR faults. | Fixed | 8d313de
R2-S5 | 2 | 4abca60 | export_pdf.py | find_browser (~33) | Suggestion | Style | import os nested inside the function while all other imports are top-level. | Fixed | 8d313de
R2-S6 | 2 | 4abca60 | export_pdf.py | export (~44) | Suggestion | Correctness | --virtual-time-budget support is patchy in new headless mode; needed verification on Brave. | Closed - not an issue
R2-S7 | 2 | 4abca60 | .gitignore | - | Suggestion | Style | Missing __pycache__/, .DS_Store and CONTEXT.md entries. | Fixed | 8d313de
R2-S8 | 2 | 4abca60 | render_html.py | - | Suggestion | Maintainability | 393 of 400 lines with chart geometry still to be shared with render_pptx.py; extraction now urgent. | Open
R3-C1 | 3 | 2eb086e | validate.py | _is_claim (202) | Critical | Correctness | title-is-claim wrong in both directions at error severity; noun phrases pass on any lemma token, verb-less claims blocked. | Fixed | 39d155b
R3-H2 | 3 | 2eb086e | validate.py | check_chart_fit (294) | High | Correctness | Fires on standard practice: a four-quarter bar chart warns; _TEMPORAL matches any bare 4-digit string. | Fixed | 8d313de
R3-H3 | 3 | 2eb086e | validate.py | _lum (311) | High | Correctness | Crashes on any non-hex theme colour; renderer permitted named/functional colours, so the two disagreed on a legal theme. | Fixed | 8d313de
R3-H4 | 3 | 2eb086e | validate.py | main (426) | High | Correctness | A PASS did not mean the deck renders: image src existence unchecked, so a missing file died later in _embed_images. | Fixed | 8d313de
R3-S1 | 3 | 2eb086e | validate.py | check_schema (153-160) | Suggestion | Correctness | ids[cid] inserted even when cid is None, producing a spurious 'duplicate id None'. | Fixed | 8d313de
R3-S2 | 3 | 2eb086e | validate.py | main (426-427) | Suggestion | Maintainability | Malformed deck.json produced a raw JSONDecodeError traceback. | Fixed | 8d313de
R3-S3 | 3 | 2eb086e | validate.py | _block_h (343) | Suggestion | Correctness | Overflow estimator constants uncalibrated by measurement while driving an error-severity finding. | Deferred - phase 8
R3-S4 | 3 | 2eb086e | validate.py | check_evidence (260) | Suggestion | Correctness | A divider counted as evidence. | Fixed | 8d313de
R3-S5 | 3 | 2eb086e | validate.py | main (422) | Suggestion | Maintainability | --passes parsed and written into findings.json but consumed by nothing. | Deferred - phase 6
R3-S6 | 3 | 2eb086e | validate.py | check_contrast (324) | Suggestion | Correctness | Only four fg/bg pairs checked; accent and the five series colours unchecked. | Fixed | 8d313de
R4-C1 | 4 | 8d313de | validate.py | _is_claim (226) | Critical | Correctness | Casing heuristic enforced casing, not claim-ness, at error severity; self-defeating - rewards sentence case, in which the noun-phrase detector collapses. | Fixed | 39d155b
R4-H2 | 4 | 8d313de | export_pdf.py | export (~55) | High | Correctness | pages != cards cannot detect card overflow, so it does not backstop the estimator as claimed. | Fixed | 39d155b
R4-H3 | 4 | 8d313de | export_pdf.py | export (~57) | High | Maintainability | Page counting couples the exporter to renderer markup; /Type /Page regex misses compressed object streams, risking a hard wrong failure. | Fixed | 39d155b
R4-H4 | 4 | 8d313de | validate.py | IR_DIR (68,486) | High | Test coverage | IR_DIR global set only by main(), so the library path silently skipped the image gate that phase 10's harness would exercise. | Fixed | 39d155b
R4-M5 | 4 | 8d313de | render_html.py | _legend (64) | Medium | Correctness | Two-row cap broke silently: with 12 series four bars rendered with no legend entry. | Fixed | 39d155b
R5-M1 | 5 | 39d155b | validate.py | _is_claim | Medium | Correctness | Four residuals on 30 unseen titles (26/30 correct). False positives: 'Product Launch Timeline', 'Onboarding Funnel Drop Off'. False negatives (block valid decks): 'Latency regressions correlate...', 'Support costs scale...', 'Pricing power sits...'. Open-class lexicon gap. | Open
R5-M2 | 5 | 39d155b | render_html.py | _legend / _ser (64) | Medium | Correctness | _ser cycles at 5 colours, so the 10 legend entries drawn for a 12-series chart contain duplicate swatches; ambiguity above 5 series is silent. | Open
R5-L3 | 5 | 39d155b | render_html.py | _legend (60) | Low | Style | Comment says 'cap at two rows' but the function returns rows=3 for 12 series; behaviour correct, comment stale. | Open
R5-A1 | 5 | 39d155b | BUILD-SPEC.md | section 10 | Action | Maintainability | Recommendation: demote title-is-claim to warn and move claim detection to the phase-6 judge as error. Spec-owner call; decide before phase 7 since the playbooks will be written to whatever this check rewards. | Open
R6-H1 | 6 | da764c2 | report.py | _scores (34-41) / report_md (136-140) | High | Correctness | No score-range validation on LLM output: a judge returning storyline=9 yields 'Mean 5.0 / 5' - a mean above the maximum, printed without comment. Section 11 defines a 1-5 scale. | Open
R6-H2 | 6 | da764c2 | report.py | _scores (36-37) | High | Correctness | A missing dimension is silently absent: four of five dimensions gave 'Mean 4.0 / 5, lowest 4 - PASS' with no sign density was never scored. Shrinking the denominator rewards a judge that omits its worst dimension. | Open
R6-M3 | 6 | da764c2 | report.py | _scores (38-40) | Medium | Correctness | Unknown dimensions are averaged into the section 11 gate: an invented 'newDim: 1' shifted the mean and became the reported 'lowest'. | Open
R6-M4 | 6 | da764c2 | report.py | inline_summary (69) | Medium | Maintainability | Kind extraction parses prose - PLURAL[message.split(' ')[0]] - so it works only for validate.py's current wording; 'placeholder data used in a chart' degraded to 'values on c4'. Read block type from the finding instead. | Open
R6-M5 | 6 | da764c2 | report.py | inline_summary (70-72) | Medium | Style | A card-less unverified finding renders 'tables on use placeholder data' - double space, dangling preposition. | Open
R6-M6 | 6 | da764c2 | report.py | report_md (135) | Medium | Correctness | Judge notes interpolated into the markdown table unescaped: a note containing a pipe splits the row into extra columns (verified). | Open
R6-L7 | 6 | da764c2 | report.py | report_md (121-127) | Low | Style | No cap at section 11's five concerns; nine rendered without truncation or a contract-violation flag. | Open
R6-A2 | 6 | da764c2 | report.py | _scores / report_md | Action | Maintainability | Design call: handle a structurally invalid judge.json under one mechanism - a 'judge-contract' finding surfaced in section 2 - rather than four separate guards. Would cover R6-H1, H2, M3 and L7. | Open
R6-A3 | 6 | da764c2 | BUILD-SPEC.md | section 12 | Action | Maintainability | Document the convention that info findings fold into section 3 under 'Also noted' - section 12 says info is surfaced only in report.md but gives it no section, and phase 10 expected-output files will assert against it. | Open

## Summary
Summary
Every figure is a COUNTIF over 'Issue Register' - edit that sheet and these update.
By severity
Severity | Count
Critical | 6
High | 13
Medium | 7
Low | 2
Suggestion | 25
Action | 3
Total | 56
By status
Status | Count
Fixed | 37
Open | 16
Deferred - phase 6 | 1
Deferred - phase 8 | 1
Closed - not an issue | 1
Total | 56
By review round
Round | Count
1 | 17
2 | 11
3 | 10
4 | 5
5 | 4
6 | 9
Total | 56
By category
Category | Count
Correctness | 33
Security | 2
Performance | 1
Maintainability | 12
Style | 6
Test coverage | 2
Total | 56
Still open
Open items only, by severity (blocking work for phase 6 onward):
Severity | Open count
Critical | 0
High | 2
Medium | 6
Low | 2
Suggestion | 3
Action | 3